## Sprint 2
Time Box : 2 (7th Sept to 20th Sept)
Sl No | Feature | Sub Feature | Task | Estimate(days) | Capacity(Resource) | Acceptance Criteria | names
| SDET | TestPlan
|  | Automation | 1.FrameWork Design 2. Build Common Features 3.Test Suit Execution ( CI / CD )
1 | Search | 1.Wild Card Search | 1.Implement wild search on existing search algorithm 2. Test Scenario/ Test Case Writing and Test Case Review 3. Risk Analysis and Mitigation 4. Test Execution / Retest (for fixed defects). 5.Automation Script Development | 5 + 2 | 2 | Working wild card search | Soumodip & Srinivas
2 | Filters | 1. Filter data based on Difficulty 2. Filter data based on Course Type 3. Filter data based on Course Price 4. Filter data based on Certification 5. Filter data based on Tags 6. Filter data based on Course Duration | 1.Implement the filters on existing search 2. Test Scenario/ Test Case Writing and Test Case Review 3. Risk Analysis and Mitigation 4. Test Execution / Retest (for fixed defects). 5.Automation Script Development | 4 + 2 | 2 | Search results based on filters | Gursimran & Supreeth
3 | Sorting | 1.Sort based on Course Price 2.Sort based on Course Ratings | 1.Implement price and rating parameters on sort. 2. Test Scenario/ Test Case Writing and Test Case Review 3. Risk Analysis and Mitigation 4. Test Execution / Retest (for fixed defects). 5.Automation Script Development | 4+ 2 | 2 | Search results displayed on the basis of sorting preference | Saloni & Mehak
4 | Login/Sign Up | 1. Google/Facebook/Azure integration | 1.Implement google/ Facebook/ Azure API's inthe Login procedure 2. Test Scenario/ Test Case Writing and Test Case Review 3. Risk Analysis and Mitigation 4. Test Execution / Retest (for fixed defects). 5.Automation Script Development | 4+ 2 | 2+2 | Login using Google/ Facebook/ Azure. | carson/bhagya & Gautam
5 | Dashboard | 1.Widgets,Wishlist | 1.Include widgets to the dashboard. 2.Button to add a Course for later interest. | 5 | 1 | Working wishlist button | Bishal
6 | Query Box | 1. Add a query system with drop a mail button and call button | Include query buttons like contact us and drop a mail. | 4 | 1 | Working contact us and drop a mail button | Soumik
7 | Redirection | 1. Add the provider’s link. 2. Redirection system to move to the provider’s link after clicking the button Devise a receipt system to keep count | 1.Add the link for redirection system & then put a receipt system to take count of the no of clicks for adding transparency in the pay per click mode of revenue. 2. Test Scenario/ Test Case Writing and Test Case Review 3. Risk Analysis and Mitigation 4. Test Execution / Retest (for fixed defects). 5.Automation Script Development | 5+ 2 | 2 | 1.Working links 2.Working receipt system | Allavarapu & Keerthana
8 | Enhancements from Timebox 1 | User settings | 1.Implement ReactJS on Sprint 1 features. 2. Test Scenario/ Test Case Writing and Test Case Review 3. Risk Analysis and Mitigation 4. Test Execution / Retest (for fixed defects). 5.Automation Script Development | 4+ 2 | 2 | Enhancements | Manisha & Jishnu
9 | Integration | GIT Lab | 1. Combine all files worked on into one GIT project | 2 | 1 | Code integration No conflicts Version Control
10 | Deployment | Jenkins | 1.Initiate Build add check build status | 2 | 1 | Initiate Build, Retrospective build Status, Refresh Browser for updated features
11 | Client Meeting | Demo | Presenting Demo to Client | 1 | 15 | Proper Presentation Run Project on Cloud
Sl No | Feature | Sub Feature | Task | Estimate(days) | Capacity(Resource) | Acceptance Criteria | Things We Were Not Able To Complete | Names
1 | Layout (Schema/UI framework) | Schema/UI Framework | 1.Create UI Framework 2.Create DB Design 3.Create Backend Folder Structure 4.Data Modelling 5.Naming Convention | 4 | 6 | 1.UI Framework 2.DB Design 3.Backend Folder Structure 4.Data Modelling 5.Naming Convention | 1.UI Framework was not complete. 2.Team should follow more proper coding / naming convention | Layout Team
3 | User Entry | SignUp | 1.Display Signup Popup box 2.Create name field & Validate 3.Create email id field & Validate 4.Create password field & Validate 5. Create confirm Password field & validate 6. Create a signup button 7. Send verification link to email id. 8. Confirmation & landing upto dashboard | 3 | 2 | 1. Display signup popup box 2. Name, Email id, Password, Confirm Password & Validate 3. Signup and verification mail 4. Confirmation and landing upto dashboard | 1.Confirm Password not created 2. Validations we nont there. 3.Back-end was not ready. [ data storing, verification,redirection] | Carson
|  | Login / Logout | 1.Display Login Popup box 2.Create Username Field & Validate 3.Create Password Field & Validate 4. Create Login Button 5. Create Logout button and land on the home page | 2 | 1 | 1.Display Login PopUp 2. Email Id & Validate 3. Alphanumeric password & Validate 4. Login to portal and display dashboard 5. Logout button and landing onto home page | 1. Back-end was not ready. [Authention and redirection] | Bhagya
4 | HomePage (Splash Screen) | Default landing page | 1. Create search bar 2. FAQ's, About Us, Contact Us 3. Design look and feel | 2 | 1 | 1. Search bar 2. Relevant links 3. UI look and feel | 1. No FAQ's section 2.No contact us section. | Soumik
6 | Search | Course search | 1. Fetch search query 2. Display search results 3. Design look and feel of search results | 3 | 2 | 1. Fetch search query 2. Display search results 3. Design look and feel of search results | 1.Display Search results. [ cards display and redirection] | GurUs
8 | Settings | User settings | 1. Edit / update user email id 2. Edit / update password 3. Edit / update phone number 4. Edit / update user-name | 2 | 1 | 1. Update user details - name,email id, password, phonenumber etc | 1.No edit or update section | Manisha

## Sprint1
Time Box : 1
Sl No | Feature | Sub Feature | Task | Estimate(days) | Capacity(Resource) | Acceptance Criteria | Things We Were Not Able To Complete | Names
1 | Layout (Schema/UI framework) | Schema/UI Framework | 1.Create UI Framework 2.Create DB Design 3.Create Backend Folder Structure 4.Data Modelling 5.Naming Convention | 4 | 6 | 1.UI Framework 2.DB Design 3.Backend Folder Structure 4.Data Modelling 5.Naming Convention | 1.UI Framework was not complete. 2.Team should follow more proper coding / naming convention | ui
|  | Spring MVC Setup | 1.Create Spring MVC Setup | 4 | 3 | 1. Spring MVC Setup | Done or we can say no impediments as of now
2 | Project Setup | GIT | Create a new repository, Create a branch | 1 | 1 | 1. Code Integration 2. Version Control, No conflicts | Done or we can say no impediments as of now
|  |  | Code Checkout |  |  |  | Done or we can say no impediments as of now
|  | Cloud | Setup/Config Cloud Environment for DB | 2 | 1 |  | Done or we can say no impediments as of now
|  |  | Setup/Config Cloud Environment for Service Side |  |  |  | Done or we can say no impediments as of now
|  |  | Setup/Config Cloud Environment for Client Side |  |  |  | Done or we can say no impediments as of now
|  | CI/CD | Setup Jenkins for project | 2 | 1 |  | Done or we can say no impediments as of now
3 | User Entry | SignUp | 1.Display Signup Popup box 2.Create name field & Validate 3.Create email id field & Validate 4.Create password field & Validate 5. Create confirm Password field & validate 6. Create a signup button 7. Send verification link to email id. 8. Confirmation & landing upto dashboard | 3 | 2 | 1. Display signup popup box 2. Name, Email id, Password, Confirm Password & Validate 3. Signup and verification mail 4. Confirmation and landing upto dashboard | 1.Confirm Password not created 2. Validations we nont there. 3.Back-end was not ready. [ data storing, verification,redirection] | bhagya+carson
|  | Login / Logout | 1.Display Login Popup box 2.Create Username Field & Validate 3.Create Password Field & Validate 4. Create Login Button 5. Create Logout button and land on the home page | 2 | 1 | 1.Display Login PopUp 2. Email Id & Validate 3. Alphanumeric password & Validate 4. Login to portal and display dashboard 5. Logout button and landing onto home page | 1. Back-end was not ready. [Authention and redirection] | manisha
4 | HomePage (Splash Screen) | Default landing page | 1. Create search bar 2. FAQ's, About Us, Contact Us 3. Design look and feel | 2 | 1 | 1. Search bar 2. Relevant links 3. UI look and feel | 1. No FAQ's section 2.No contact us section. | soumik
5 | Dashboard | User dashboard | 1. Create widgets / cards 2. Load widgets / cards data with rest APIs | 3 | 2 | 1. Widgets / cards 2. Logged in users relevant data vis-à-vis widgets | 1. Fetching the data with rest Api but not completely. | bishal
6 | Search | Course search | 1. Fetch search query 2. Display search results 3. Design look and feel of search results | 3 | 2 | 1. Fetch search query 2. Display search results 3. Design look and feel of search results | 1.Display Search results. [ cards display and redirection] | soumodip
7 | Course description page | Course description page | 1. Fetch data of selected course from search result 2. Display all relevant data related to course 3. Design look and feel of course page 4. Create a providers button 5. Create watch later button | 2 | 2 | 1. Fetch data of selected course from search result 2. Display all relevant data related to course 3. Design look and feel of course page 4. Redirect to providers page 5. Update watch later list | 1. Static data was displayed in case of dynamic data i.e. data not fetching from DB. 2.No redirection was there from the buttons. | harish--
8 | Settings | User settings | 1. Edit / update user email id 2. Edit / update password 3. Edit / update phone number 4. Edit / update user-name | 2 | 1 | 1. Update user details - name,email id, password, phonenumber etc | 1.No edit or update section | manisha
9 | Integration | GIT Lab | 1. Combine all files worked on into one GIT project | 2 | 1 | Code integration No conflicts Version Control | 1.Last moment integration created chaos. 2.Need time management . 3.Regular push and pull
10 | Deployment | Jenkins | 1.Initiate Build add check build status | 2 | 1 | Initiate Build, Retrospective build Status ,Refresh Browser for updated features | 1. Few components were not deplayed.
11 | Client Meeting | Demo | Presenting Demo to Client | 1 | 15 | Proper Presentation Run Project on Cloud